## Slide 1: USACE Philadelphia District MAC Meeting
MAC Meeting Presentation
Michael A. Landis, Chief Operations Division
Timothy J. Kelly, P.E., Deputy Chief Operations Division
Timothy J. Rooney, Project Manger
09September2021

## Slide 2
Delaware River, Philadelphia to Sea
The current annual maintenance dredging being performed by Norfolk Dredging Company (NDC) has completed New Castle (NC) Range and NDC is currently working in Marcus Hook (MH) Range.
The next annual maintenance dredging contract is consolidated with Wilmington Harbor. It has been advertised and bid opening is scheduled for 13 September 2021. Dredging operations will begin at Wilmington Harbor then Delaware River. The ranges anticipated to be dredged in the Delaware River are NC, MH, Cherry Island/Bellevue, and Deepwater Point Ranges.
An object removal contract has been advertised on 28Aug2021 to remove rock in Bellevue and MH Ranges. There are options for Billingport widener, obstruction removal, Reedy/Baker and Liston Ranges. Bid Opening is for scheduled for 27Sept2021.
The Hopper Dredge McFarland is scheduled to be in the shipyard for steel work. The McFarland is anticipated to be out of the shipyard in Spring of 2022.

## Slide 3
Delaware River, Philadelphia to Trenton
A contract (bucket only) to dredge the lower 40-foot project to address edge shoals was advertised on 3 August with bid opening scheduled for 10 September.
Wilmington Harbor
Maintenance dredging is consolidated again with the Philadelphia to Sea Maintenance Dredging Solicitation advertised on 12 August, with bid opening currently scheduled for 13 September.